## Devs
|  | State | Market | Grocer/Anchor Tenant | Dev Start | Anchor Opens | Estimated Net Development Costs After JV Buyout | Est. Net Costs to Complete (1) | % of Costs Incurred | Development Yield Before JV Buyout (4) | Completion Yield | Completion Year Yield Qtr/Year | Return After JV Buyout | GLA | % Leased | Gross GLA | Gross % Leased | Before JV Actual Yield | Variance
Properties in Development:
6085101 | Ballard Blocks II (1) |  | Seattle, WA | PCC Community Markets & West Marine | Q1-2018 | 2019-06-01 | 31056762 | 10795692.84 | 16.72% | 6.3% | 0% | 0 | 6.3% | 114004 | 57.27% | 213846 | 96.89% | 6.308% | -0.007876%
60786 | Chimney Rock |  | New York, NY | Whole Foods, Nordstrom Rack & Saks Off 5th | Q4-2016 | 2018-03-01 | 70872096.02 | 10795692.84 | 89.93% | 6.54% | 0% | 0 | 6.54% | 217871 | 90.26% | 213846 | 96.89% | 6.642% | -0.1018%
60773 | Indigo Square |  | Charleston, SC | Publix Greenwise Market | Q4-2017 | 2019-02-01 | 16574178.45 | 10795692.84 | 39.74% | 8.3% | 0% | 0 | 8.3% | 51071 | 71.2% | 0.71195 |  | 8.204% | 0.09593%
6079001 | Market at Springwoods Village (2) |  | Houston, TX | Kroger | Q1-2016 | 2017-05-01 | 14160197.7341 | 10795692.84 | 87.28% | 9.3% | 0% | 0 | 9.3% | 167231 | 89.37% |  |  | 9.173% | 0.1272%
60744 | Mellody Farm | IN | Chicago, IL | Whole Foods, Nordstrom Rack & REI | Q2-2017 | 2018-10-01 | 103162190 | 10795692.84 | 44.26% | 6.784% | 0% | 0 | 6.784% | 252314 | 63.81% | 213846 | 96.89% | 6.784% | 0%
6074201 | Midtown East (3) | IN | Raleigh, NC | Wegmans | Q4-2017 | 2019-09-01 | 22048110.9755 | 10795692.84 | 37.37% | 8% | 0% | 0 | 8% | 173936 | 75.1% | 213846 | 96.89% | 7.909% | 0.09058%
60770 | Northgate Marketplace Ph II | IN | Medford, OR | Dick's & HomeGoods | Q4-2015 | 2016-10-01 | 40790909.42 | 10795692.84 | 98.05% | 7.3% | 0% | 0 | 7.3% | 176910 | 91.86% | 213846 | 96.89% | 7.312% | -0.01234%
60751 | Pinecrest Place | IN | Miami, FL | Whole Foods | Q1-2017 | 2018-01-01 | 16429495.84 | 10795693.84 | 33.79% | 7.3% | 0% | 0 | 7.3% | 69652 | 74.59% | 213847 | 96.89% | 7.377% | -0.07744%
60669 | The Field at Commonwealth |  | Metro DC | Wegmans | Q1-2017 | 2018-08-01 | 45213189.61 | 10795693.84 | 71.2% | 7.5% | 0% | 0 | 7.5% | 187130 | 86.73% |  |  | 7.489% | 0.01094%
60750 | The Village at Riverstone |  | Houston, TX | Kroger | Q4-2016 | 2018-10-01 | 30657658.8112 | 10795693.84 | 56.81% | 8% | 0% | 0 | 7.8% | 165134 | 86.94% |  |  | 8.151% | -0.1515%
| Total Properties in Development |  | 10 |  |  |  | 390964788.8609 | 107956931.3995 | 60.6% | 7.179% | 7.865% |  | 7.2 (5) | 1575253 | 79.97% | 1283077.712 | 83.38%
| NOI from Properties in Development (Current Quarter) | [5 empty] | 899116.03
| Base rent from Development Completions for leases signed but not yet rent-paying (Current Quarter) | [5 empty] | 0
Notes:
New starts for the quarter are in bold and italicized.
See Page 30 for additional disclosures regarding undeveloped land classified on the balance sheet as Land, building, and improvements, rather than Properties in Development.
(1) Reflects Regency's share of Estimated Net Development Costs After JV Buyout at 49.9% noncontrolling interest.
(2) Reflects Regency's share of Estimated Net Development Costs After JV Buyout at 53% controlling interest. Anchor rent commencement date is May-2017. Anchor opening date is Nov-2017.
(3) Reflects Regency's share of Estimated Net Development Costs After JV Buyout at 50% noncontrolling interest.
(4) Represents the ratio of Regency's underwritten NOI at stabilization to total estimated net development costs, before any adjustments for expected JV partner buyouts.
(5) After allocating land basis for outparcel proceeds, additional interest and overhead capitalization, returns are estimated to be 6.5% for Projects in Development.
Note on K8: Angela Coker: Reflecting actual yield; not applying rounding rule

## Redev
Property Name | Market | Description | Grocer/Anchor Tenant | Target Completion Year (1) | Incremental Costs (2) | % of Costs Incurred | Incremental Yield
Properties in Redevelopment (>$5M):
Countryside Shops | Miami | Relocation and expansion of existing Publix including reduction of shop space and leasing former Publix space to Ross; addition of pad building leased to Chipotle; refaçade remaining center. | Publix | 2018 | 21337443.7 | 69.53% | 6% - 7%
Paces Ferry Plaza | Atlanta | Reconfiguration of center including construction of Whole Foods 365, parking deck, and façade renovations. | Whole Foods 365 | 2018 | 15162205.67 | 68.76% | 9% - 10%
Point Royale Shopping Center | Miami | Reconfiguration of the former Best Buy space for Burlington Coat and two junior anchors; construction of new outparcel leased to Panera Bread; façade enhancements to remaining center. | Winn Dixie | 2018 | 10935277 | 64.77% | 7% - 8%
Various Properties | 6 | Redevelopments located in various markets with project costs <$5M |  |  | 15890513.868 | 51.14% | 7% - 10%
Total Properties in Redevelopment | 9 |  |  |  | 63325440.238 | 62.35% | 7% - 9%
Redevelopment Completions (>$5M):
Serramonte Shopping Center | San Francisco | Additional 250K SF of new retail including new parking deck. Anchor leases executed with Nordstrom Rack, Ross, TJ Maxx, Buy Buy Baby, Cost Plus World Market, Dave & Busters and Daiso. | Buy Buy Baby, Dave & Buster's, Nordstrom Rack, Ross Dress For Less, TJ Maxx | 2018 | 116200000 | 91.31% | 6% - 7%
Various Properties | 4 | Redevelopments located in various markets with project costs <$5M |  |  | 10524487.95 | 92.5% | 7% - 10%
Total Redevelopment Completions | 5 |  |  |  | 126724487.95 | 91.45% | 6% - 7%
Reconciliation of Summary of Development and Redevelopment to Properties In Development (Balance Sheet):
Developments | % of estimated development costs, including GAAP allocations |  |  |  | 261098000
Redevelopments | % of incremental costs |  |  |  | 39485952.2487
Other Costs | Pre-development costs and accruals for costs not yet paid |  |  |  | 39068246.8843
Transfers to Operating | Cost of assets placed in service |  |  |  | -142089707.91
Properties in Development (Pro-Rata) |  |  |  |  | 197562491.223
(1) Target completion year reflects the year that construction is expected to be substantially complete.
(2) Includes Regency's pro-rata share of unconsolidated co-investment partnerships.